Software Engineering Lab

Group Number – 22

Group Members :-

Ishwari Mahajan- 202301040173

Omkar Londhe - 202301040027

Sneha Nannaware- 202301040267

Yashraj Jagtap- 202301040092

Om Thorat - 202301040155

Sumit Khetre – 202401040017

Company Details – Organization: Senim Solutions LLP

Name: Pravin Pawane (CEO - pravin.pawane@senim.in )

Location: Bhosari , Pune

Assignment :- Prepare a suitable cost estimation model, WBS, Gantt chart (using MS project tool) and all

neces- sary estimation for your project

Project Details – Problem Statement :- Enhancing company registration security by implementing real-time

camera-based age and gender verification to prevent fraudulent entries.

1. Executive Summary

This Project Management Plan outlines the complete cost estimation, Work Breakdown Structure (WBS), Gantt chart schedule, and all necessary project estimations for the Resume & Credential Fraud Detection Platform. The system is a web-based AI-driven platform designed to detect fraudulent resumes, manipulated certificates, and suspicious employment histories during the recruitment process. The platform integrates NLP-based resume parsing, computer vision-based certificate verification, company authentication, metadata analysis, and a weighted fraud risk scoring engine all accessible through a recruiter dashboard and ATS REST API.

| Parameter | Details |
| --- | --- |
| Project Name | Resume & Credential Fraud Detection Platform |
| Project Type | Web-Based AI Application (Academic Project) |
| Team Size | 6 Members |
| Duration | 12 Weeks (3 Months) |
| Total Estimated Cost | 2,18,500 (approx.) |
| Technology Stack | React.js, Spring Boot, Python (NLP/OpenCV), PostgreSQL, Docker, AWS |
| Estimation Model | COCOMO II + Function Point Analysis |

## 2. Cost Estimation Model

Note: The Function Points and SLOC have been adjusted to reflect the actual size of a Flask/OpenCV Computer Vision application, rather than a massive enterprise microservices system.

### 2.1 Estimation Methodology

Two complementary models are used to derive a reliable cost estimate:

- COCOMO II (Constructive Cost Model II): Estimates effort in person-months based on estimated source lines of code (KSLOC).

- Function Point Analysis (FPA): Measures functional size by counting identifiable user-visible functions.

### 2.2 Function Point Analysis

| Function Category | Count | Low Wt. | Avg Wt. | High Wt. | FP Score |
| --- | --- | --- | --- | --- | --- |
| External Inputs (EI) | 4 | 3 | 4 | 6 | 16 |
| External Outputs (EO) | 5 | 4 | 5 | 7 | 25 |
| External Inquiries (EQ) | 3 | 3 | 4 | 6 | 12 |
| Internal Logical Files (ILF) | 2 | 7 | 10 | 15 | 20 |
| External Interface Files (EIF) | 3 | 5 | 7 | 10 | 21 |
| Total UFP |  |  |  |  | 94 |

- Value Adjustment Factor (VAF): 1.05 (complex mathematical/vision processing adjustment)

- Adjusted Function Points (AFP): UFP × VAF = 94 × 1.05 ≈ 99 FP

- Conversion: 1 FP ≈ 40 SLOC (Python/Flask) → ~4,000 SLOC (4 KSLOC)

### 2.3 COCOMO II Estimation

Using the COCOMO II Intermediate Model (Organic Mode for small, experienced academic teams):

- Size (KSLOC): 4

- COCOMO Mode: Organic

- Effort Coefficient (a): 2.4

- Exponent (b): 1.05

- Calculated Effort: ~10.1 Person-Months

- Estimated Duration: ~2.3 Months (Approx 10-12 weeks)

- Required Team Size: ~4-6 members

## 3. Work Breakdown Structure (WBS)

This has been tailored to reflect your actual project modules: Flask routing, OpenCV DNN integration, Webcam feeds, and Docker/Testing.

| WBS ID | Work Package / Task | Duration | Start Wk | Owner |
| --- | --- | --- | --- | --- |
| 1 | PROJECT INITIATION & PLANNING | 2 weeks | W1 | All |
| 1.1 | Define project scope (Age & Gender Detection) | 3 days | W1 | PM/Team |
| 1.2 | Technology stack finalization (Flask, OpenCV) | 2 days | W1 | Devs |
| 1.3 | Risk assessment and mitigation plan | 2 days | W1 | PM |
| 1.4 | Resource allocation and role assignment | 1 day | W2 | PM |
| 2 | REQUIREMENTS & DESIGN | 2 weeks | W3 | All |
| 2.1 | Detailed UI/UX requirement review | 2 days | W3 | All |
| 2.2 | Data flow design for Webcam & Upload streams | 2 days | W3 | Backend |
| 2.3 | Pre-trained Model selection (Caffe/TF) review | 3 days | W3 | ML Eng |
| 2.4 | UI/UX wireframe design (Landing & Webcam pages) | 3 days | W4 | UI/UX |
| 3 | IMPLEMENTATION - FRONTEND & BACKEND | 2 weeks | W5 | Dev Team |
| 3.1 | Frontend HTML/CSS implementation | 4 days | W5 | UI/UX |
| 3.2 | Backend setup (Flask routing) | 3 days | W5 | Backend |
| 3.3 | Image Upload handling module | 3 days | W6 | Backend |
| 4 | IMPLEMENTATION - COMPUTER VISION MODULES | 2 weeks | W7 | Dev Team |
| 4.1 | Integrate SSD Face Detection network (.pb) | 3 days | W7 | ML Eng |
| 4.2 | Integrate Gender Classification (.caffemodel) | 2 days | W7 | ML Eng |
| 4.3 | Integrate Age Classification (.caffemodel) | 2 days | W8 | ML Eng |
| 4.4 | Implement real-time bounding box annotations | 3 days | W8 | ML Eng |
| 5 | TESTING & QA (Senim Solutions) | 2 weeks | W9 | QA |
| 5.1 | Pytest & Selenium framework setup | 2 days | W9 | QA |
| 5.2 | Test webcam streams and file uploads (TC01-TC04) | 3 days | W9 | QA |
| 5.3 | Edge case testing (No face, under-age, spoofing) | 3 days | W10 | QA |
| 5.4 | Bug fixing and threshold adjustments | 2 days | W10 | All |
| 6 | DEPLOYMENT & CLOSURE | 2 weeks | W11 | DevOps |
| 6.1 | Docker containerization (Dockerfile creation) | 3 days | W11 | DevOps |
| 6.2 | Cloud/Local hosting setup & Documentation | 3 days | W11 | DevOps |
| 6.3 | Final report and project presentation | 4 days | W12 |  |

### 3. Gantt Chart — MS Project Import Data

### 4. Comprehensive Project Estimations

#### 4.1 Risk Register & Mitigation

| Risk | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Low lighting / Poor camera quality | High | High | Implement front-end checks requesting the user to move to a well-lit area before capturing. |
| Presentation Attacks (Spoofing) | Medium | High | Integrate liveness detection checks (e.g., blink detection) in the ML pipeline. |
| High GPU Cloud Costs | Medium | Medium | Optimize the ML model size (e.g., using MobileNet architectures) and terminate idle instances. |
| Latency in Prediction | Medium | High | Process frames asynchronously; show a loading animation on the frontend so the user doesn't refresh. |

#### 4.2 Quality Metrics & Acceptance Criteria

| Quality Metric | Target | Measurement Method |
| --- | --- | --- |
| Model Accuracy | >90% | Validation against testing datasets for age variance and gender. |
| Inference Latency | < 500ms | Track the time from frame capture to API response. |
| System Uptime | 99.9% | Cloud hosting monitoring tools. |
| False Rejection Rate | < 5% | Monitor failed verifications that require manual override. |

#### 4.3 Assumptions & Constraints

- Assumptions: All 6 group members will be available for the entire 12-week timeline. Senim Solutions will provide clear feedback during the UAT phase.

- Constraints: High-accuracy real-time video processing requires adequate hardware, placing a constraint on utilizing strictly free-tier cloud services. The system must operate smoothly across standard web browsers without requiring users to install native applications.