## Exporting Tables to Excel
REF / ID | Pre-Mitigation |  |  |  | DEPARTMENT / LOCATION | MITIGATIONS / WARNINGS / REMEDIES | Post Mitigation
| RISK | RISK SEVERITY | RISK LIKELIHOOD | RISK LEVEL |  |  | Risk Severity | RISK LIKELIHOOD | RISK LEVEL (POST) | ACCEPTABLE TO PROCEED?
R01 | Presentation Attack (Spoofing): User holds up a photo or video to the camera instead of their live face to bypass security. | INTOLERABLE | PROBABLE | EXTREME | AI / Security | Implement AI-based liveness detection and anti-spoofing algorithms to detect depth and micro-movements. | TOLERABLE | IMPROBABLE | LOW | YES
R02 | Algorithmic Bias: The ML model shows lower age/gender accuracy for specific ethnicities or skin tones. | UNDESIRABLE | POSSIBLE | HIGH | AI / ML Data | Train the TensorFlow/PyTorch models on highly diverse, globally representative datasets. Flag low-confidence predictions for manual review. | TOLERABLE | IMPROBABLE | MEDIUM | YES
R03 | Environmental Failures: Face detection fails due to poor user lighting or low camera resolution (<720p). | UNDESIRABLE | PROBABLE | HIGH | UI/UX & Frontend | Add UI prompts detecting low light and asking the user to adjust. Provide a fallback option for manual review. | ACCEPTABLE | PROBABLE | LOW | YES
R04 | Data Privacy Violation: User biometric images are stored permanently or leaked, violating GDPR/COPPA. | UNDESIRABLE | POSSIBLE | EXTREME | Compliance / Database | Enforce ephemeral storage (auto-delete after verification). Encrypt data at rest (AES-256) and hash images (SHA-256). | ACCEPTABLE | IMPROBABLE | LOW | YES
R05 | High Processing Latency: AI image processing takes longer than the 2-3 second threshold, causing user drop-off. | UNDESIRABLE | POSSIBLE | MEDIUM | Backend / Cloud | Optimize model sizes (quantization). Route heavy processing to CUDA-enabled GPU cloud instances. Show loading animations on UI. | ACCEPTABLE | IMPROBABLE | LOW | YES
R06 | API Integration Downtime: The RESTful API fails to connect with the existing company registration portal. | TOLERABLE | POSSIBLE | MEDIUM | API / Integration | Implement robust error handling, automated retry logic, and queue failed verification logs to sync when the portal is back online. | ACCEPTABLE | IMPROBABLE | LOW | YES
R07 | System Overload: High traffic exceeds the targeted 500+ verifications/hour, causing system crashes. | UNDESIRABLE | POSSIBLE | MEDIUM | DevOps / Infrastructure | Implement horizontal scaling, load balancers, and automatic failover mechanisms to maintain 99.9% uptime. | ACCEPTABLE | IMPROBABLE | LOW | YES
R08 | Hardware/Permission Block: The user's browser or OS denies web camera access, halting registration. | TOLERABLE | PROBABLE | MEDIUM | Frontend | Provide clear, step-by-step UI instructions on how to enable camera permissions in various browsers. | ACCEPTABLE | POSSIBLE | LOW | YES
R09 | Man-in-the-Middle (MitM) Attack: Verification data or API keys are intercepted over the network. | INTOLERABLE | IMPROBABLE | HIGH | Network Security | Enforce strict HTTPS (TLS 1.3), WebSockets security, and JWT (JSON Web Tokens) for all API authentication. | ACCEPTABLE | IMPROBABLE | LOW | YES
R10 | False Positive Lockouts: The "24-hour block" rule incorrectly triggers for genuine users who struggled with the UI. | UNDESIRABLE | POSSIBLE | MEDIUM | Business Logic | Implement dynamic retry thresholds. Allow users to switch to a manual document upload before enforcing a hard 24-hour ban. | TOLERABLE | IMPROBABLE | LOW | YES